## Tabelle1
Risk	Description	Prob. Of Occurrence	Impact	Factor	Mitigation Strategy	Person in Charge
User doesn’t have enough keys / to play the game	self explanatory	80,00 %	8	6,4	customize key bindings, extend possible key bindings / Beyond one input peripheral	Philipp
technical difficulties	we have major problems implementing / different use cases	45,00 %	8	3,6	more research	Dominik
architecture extensibility	missing expertise with component based / Architecture might lead to obscure structure	60,00 %	6	3,6	refactoring	Leon
Getting sidetracks by less / Important issues	too much work goes in hard to imple- / Ment but uncritical game mechanics/details	95,00 %	3	2,85	regularily check time estimation and act accordingly	Leon
loveless graphics	due to limited time, graphics could suffer	85,00 %	3	2,55	use free assets	Philipp
Too much work in a sprint	too many issues lead to unrealistic / Amount of work	80,00 %	3	2,4	Add realistic amount of work to a sprint	Dominik
game mechanics don’t work out	some thought out game mechanics / Might not work out	90,00 %	2	1,8	spend more time planning / come up with viable alternatives	Lukas
hard deployment	due to missing expertise with Unity, / Deployment might be difficult	25,00 %	7	1,75	more research	Dominik
The game is not fun	nobody wants to play the game / Because it’s no fun	20,00 %	8	1,6	Add unicorns or be sad	Leon
balancing	without proper balancing, risk 3 might occur	40,00 %	4	1,6	play testing	Lukas
Unable to meet sprint deadline	there is not enough time to finish / Sprint tasks	30,00 %	4	1,2	- good scheduling / - reduce sprint scope/set realistic scope	Philipp
unexpected breakdowns	due to illness, hardware or infrastructural / Failures	10,00 %	10	1	N/A	Lukas